## Sheet1
| Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes | Dev 1 : Nguyễn Thanh Huy
Layout (header, carousel, intro, about company) | 28/07/2023 | 28/07/2023 | 100% | Dev 1 | 29/07/2023 | 29/07/2023 | 100% | Dev1 | Complete layout | Dev 2 : Nguyễn Đình Tín
update carousel, update about, update counterUp | 29/07/2023 | 29/07/2023 | 100% |  | 30/07/2023 | 30/07/2023 | 100% |  | Add counterUp + add darkmode button
Reponsive + nightmode | 30/07/2023 | 2023-08-01 | 100% |  | 2023-08-01 | 2023-08-01 | 100% |  | Complete 100%
Layout (featured cases, testimonials, footer, backToTop) | 28/07/2023 | 2023-08-10 | 100% | Dev 2 | 2023-08-10 | 2023-08-10 | 100% | Dev2 | Complete layout
Nightmode | 2023-08-07 | 2023-08-10 | 100% |  | 2023-08-10 | 2023-08-10 | 100% |  | Complete nightmode
Reponsive |  |  | 0% |  |  |  | 0% |  | Unbegun